## POAM
POAM ID | Weakness Description | Associated Risk | Affected System | NIST Control | Severity | Planned Remediation | Responsible Party | Milestone | Scheduled Completion Date | Current Status | Comments
POAM-001 | Users susceptible to phishing emails | Credential Theft | Microsoft 365 | AT-2, SI-4 | Critical | Implement phishing simulations and enhanced email filtering | IT Security | Deploy phishing platform | 2026-06-30 | Open | Annual awareness training currently in place
POAM-002 | Delayed critical patch deployment | Vulnerability Exploitation | Windows Endpoints | SI-2, CM-6 | High | Automate patch management and reduce deployment window | IT Operations | Implement centralized patching | 2026-07-15 | In Progress | Current remediation window averages 30 days
POAM-003 | Limited privileged account monitoring | Unauthorized Administrative Access | Active Directory | AC-6, AU-6 | High | Deploy privileged access monitoring tools | Compliance Department | Quarterly admin reviews | 2026-08-01 | Planned | Manual reviews currently performed
POAM-004 | No formal vendor risk assessment process | Third-Party Vendor Compromise | Cloud Services | SR-3, CA-3 | Moderate | Develop vendor assessment procedures | Compliance Department | Create vendor templates | 2026-08-20 | Open | Vendor contracts currently reviewed
POAM-005 | Backup restoration testing not performed regularly | Recovery Failure | Backup Systems | CP-9, CP-10 | High | Conduct quarterly restoration testing | IT Operations | Validate backup recovery | 2026-06-25 | In Progress | Daily backups operational
POAM-006 | Incomplete endpoint detection coverage | Ransomware Infection | Corporate Endpoints | SI-3, SI-4 | Critical | Expand EDR deployment to all systems | IT Security | Complete endpoint onboarding | 2026-06-20 | Open | Current coverage approximately 70%
POAM-007 | Overly permissive cloud sharing settings | Unauthorized Data Exposure | SharePoint Online | AC-3, SC-7 | High | Restrict external sharing permissions | Cloud Administration | Review external sharing settings | 2026-07-10 | Open | External sharing enabled organization-wide
POAM-008 | Incident response exercises not conducted | Ineffective Incident Response | Organization Wide | IR-3, IR-8 | Moderate | Conduct ransomware tabletop exercises annually | Compliance Analyst | Schedule tabletop exercise | 2026-09-01 | Planned | Incident response plan exists but is untested