## Risk Register
Risk ID | Risk Category | Threat | Vulnerability | Affected Asset | Likelihood | Impact | Risk Level | Existing Controls | Recommended Remediation | Risk Owner | Target Remediation Date | Status
R-001 | Phishing | Credential Theft | User susceptibility to phishing emails | Microsoft 365 Accounts | High | High | Critical | MFA, Email Filtering, Security Awareness Training | Conduct phishing simulations and improve awareness training | IT Security | 2026-07-01 | Open
R-002 | Ransomware | Malware Infection | Endpoint compromise through malicious attachments | Windows Endpoints | High | High | Critical | Antivirus, Daily Backups, VPN Security | Deploy EDR solution and validate backup recovery testing | IT Operations | 2026-06-15 | Open
R-003 | Access Management | Unauthorized Access | Excessive user permissions | EHR System | Medium | High | High | RBAC, Quarterly Access Reviews, MFA | Implement least privilege reviews monthly | Compliance Department | 2026-06-30 | In Progress
R-004 | Patch Management | Exploit of Vulnerable Systems | Delayed security patching | Corporate Endpoints | Medium | High | High | Patch Management Procedures, Vulnerability Scans | Reduce critical patch deployment window to 14 days | IT Operations | 2026-06-20 | Open
R-005 | Vendor Risk | Third-Party Compromise | Limited vendor security oversight | Cloud Services | Medium | Medium | Moderate | Vendor Agreements, Contract Reviews | Develop formal vendor risk management assessments | Compliance Department | 2026-08-01 | Open
R-006 | Remote Access | Unauthorized Remote Access | Weak remote endpoint security | VPN Infrastructure | Medium | High | High | VPN Encryption, MFA | Enforce device compliance checks before VPN access | IT Security | 2026-07-15 | Open
R-007 | Insider Threat | Improper Data Access | Lack of user activity monitoring | PHI Data Repositories | Low | High | Moderate | Audit Logs, Access Controls | Expand audit logging and monitoring capabilities | Compliance Department | 2026-09-01 | Planned
R-008 | Data Loss | Accidental Deletion | Improper backup validation | File Storage Systems | Medium | Medium | Moderate | Daily Backups | Conduct quarterly backup restoration testing | IT Operations | 2026-07-30 | In Progress
R-009 | Email Security | Business Email Compromise | Weak phishing detection | Executive Email Accounts | High | High | Critical | MFA, Secure Email Gateway | Implement advanced threat protection and executive phishing training | IT Security | 2026-06-10 | Open
R-010 | Compliance | HIPAA Violation | Improper PHI handling | Patient Records | Medium | High | High | HIPAA Training, Policies | Increase periodic HIPAA compliance audits | Compliance Department | 2026-08-15 | Open